## Summary
Summary

## Assumptions
Assumptions
Item # | Description
1 | If any dependent team hands off late then day for day delay
2 | No changes to existing functionality
3 | Filtering by subcategory only for blog
4 | Only supporting social media that we already have
5 | Omniture will only support what we currently have right now
6

## Estimate -Actual Hours
Estimate | A
Actual Points
Total Features | 14
0
DEVELOPMENT
SIZE | Points | Distr. | Count | Total Points | Days | Hours
XS | 1 | 10% | 9 | 9 | 18 | 144
S | 3 | 20% | 3 | 9 | 18 | 144
M | 5 | 50% | 1 | 5 | 10 | 80
L | 8 | 10% | 1 | 8 | 16 | 128
XL | 13 | 5% | 0 | 0 | 0 | 0
XXL | 21 | 5% | 0 | 0 | 0 | 0
|  | TOTAL | 14 | 31 | 62 | 496
Number of months | 1
Weeks | 4.3333
COST | Role | Percentage | Hours | Resourses | Man Weeks
| Project Manager | 10% | 60 | 0.34615 | 1.5
| Architect | 0% | 0 | 0 | 0
| Developer | 100% | 496 | 2.8615 | 12.4
| QA Engineer | 20% | 80 | 0.46154 | 2
| Bus Analyst | 20% | 80 | 0.46154 | 2
Total |  |  | 716 | 4.1308 | 17.9

## Sizes
Sizes
Everything
Total Hours By Epic
[10 empty] | XS | S | M | L | XL | XXL | Total Hours By Epic
Section | Categories | XS | S | M | L | XL | XXL |  | CHECK SUM | 1 | 3 | 5 | 8 | 13 | 21
1 | Template | 3 | 0 | 0 | 1 | 0 | 0 |  | 4 | 48 | 0 | 0 | 208 | 0 | #REF! | #REF!
2 | Content Types (Single Pages) | 3 | 0 | 0 | 0 | 0 | 0 |  | 3 | 48 | 0 | 0 | 0 | 0 | #REF! | #REF!
3 | Configuration | 3 | 1 | 1 | 0 | 0 | 0 |  | 5 | 48 | 80 | 128 | 0 | 0 | #REF! | #REF!
4 | Recipe | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 80 | 0 | 0 | 0 | #REF! | #REF!
5 | Sub-Category | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 80 | 0 | 0 | 0 | #REF! | #REF!
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
10 | miscelaneous | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
| TOTAL | 9 | 3 | 1 | 1 | 0 | 0 | 14 | 14 | 144 | 240 | 128 | 208 | 0 | #REF! | #REF!

## Features
| FEATURE |  |  | KEY
ITEM | epic_ID | story_ID | Description | Size | Key | Notes
1 | 1 |  | Template
2 | 1 | 1.1 | Home Page | L | 1L
3 | 1 | 1.2 | Archive Q&A | XS | 1XS
4 | 1 | 1.3 | Archive Blog | XS | 1XS
5 | 1 | 1.4 | Archive Guide | XS | 1XS
6 | 1 | 1.5
7 | 1 | 1.6
8 | 1 | 1.7
9 | 1 | 1.8
10 | 1 | 1.9
11 | 2 | 2 | Content Types (Single Pages)
12 | 2 | 2.1 | Q&A | XS | 2XS
13 | 2 | 2.2 | Blog | XS | 2XS
14 | 2 | 2.3 | Guide | XS | 2XS
15 | 2 | 2.4
16 | 2 | 2.5
17 | 2 | 2.6
18 | 2 | 2.7
19 | 2 | 2.8
20 | 2 | 2.9
21 | 3 | 3 | Configuration
22 | 3 | 3.1 | Home Page | XS | 3XS
23 | 3 | 3.2 | Taxonomy | M | 3M
24 | 3 | 3.3 | Menus | XS | 3XS
25 | 3 | 3.4 | Sections | S | 3S
26 | 3 | 3.5 | Widgets | XS | 3XS
27 | 3 | 3.6
28 | 3 | 3.7
29 | 3 | 3.8
30 | 3 | 3.9
31 | 4 | 4 | Recipe
32 | 4 | 4.1 | Custom Post Type OR Blog Format | S | 4S
33 | 4 | 4.2
34 | 4 | 4.3
35 | 4 | 4.4
36 | 4 | 4.5
37 | 4 | 4.6
38 | 4 | 4.7
39 | 4 | 4.8
40 | 4 | 4.9
41 | 5 | 5 | Sub-Category
42 | 5 | 5.1 | Post Type Filter by Sub-Category for Blogs | S | 5S
43 | 5 | 5.2
44 | 5 | 5.3
45 | 5 | 5.4
46 | 5 | 5.5
47 | 5 | 5.6
48 | 5 | 5.7
49 | 5 | 5.8
50 | 5 | 5.9
51 | 6 | 6
52 | 6 | 6.1
53 | 6 | 6.2
54 | 6 | 6.3
55 | 6 | 6.4
56 | 6 | 6.5
57 | 6 | 6.6
58 | 6 | 6.7
59 | 6 | 6.8
60 | 6 | 6.9
61 | 7 | 7
62 | 7 | 7.1
63 | 7 | 7.2
64 | 7 | 7.3
65 | 7 | 7.4
66 | 7 | 7.5
67 | 7 | 7.6
68 | 7 | 7.7
69 | 7 | 7.8
70 | 7 | 7.9
71 | 8 | 8
72 | 8 | 8.1
73 | 8 | 8.2
74 | 8 | 8.3
75 | 8 | 8.4
76 | 8 | 8.5
77 | 8 | 8.6
78 | 8 | 8.7
79 | 8 | 8.8
80 | 8 | 8.9
81 | 9 | 9
82 | 9 | 9.1
83 | 9 | 9.2
84 | 9 | 9.3
85 | 9 | 9.4
86 | 9 | 9.5
87 | 9 | 9.6
88 | 9 | 9.7
89 | 9 | 9.8
90 | 9 | 9.9
91 | 10 | 10 | miscelaneous
92 | 10 | 10.1 | Content Migration |  | 10
93 | 10 | 10.2 | SEO Migration |  | 10
94 | 10 | 10.3
95 | 10 | 10.4
96 | 10 | 10.5
97 | 10 | 10.6
98 | 10 | 10.7
99 | 10 | 10.8
100 | 10 | 10.9

## T Shirt
1 point is 2 days
Scale A
Key | Point | Person Days | Person Hours | Calc Weeks | Approx. Weeks
XS | 3 | 6 | 48 | 1.2 | 1
S | 5 | 10 | 80 | 2 | 2
M | 8 | 16 | 128 | 3.2 | 3
L | 13 | 26 | 208 | 5.2 | 4
XL | 21 | 42 | 336 | 8.4 | 8
XXL | 34 | 68 | 544 | 13.6 | 12
Scale B
Key | Point | Person Days | Person Hours | Calc Weeks | Approx. Weeks
XS | 1 | 2 | 16 | 0.4 | 0.5
S | 3 | 6 | 48 | 1.2 | 1
M | 5 | 10 | 80 | 2 | 2
L | 8 | 16 | 128 | 3.2 | 3
XL | 13 | 26 | 208 | 5.2 | 4
XXL | 21 | 42 | 336 | 8.4 | 8