## Sheet1
| Completed Widgets: | Notes | Status | Assignee | Priority | Due
1 | [1.0] Featured Blog Post |  | done
2 | [2.0] Featured Buying Guide |  | done
3 | [3.0] Featured Question (Landing Page) | need backend | done
5 | [5.0] Featured Team Members |  | done
9 | [9.0] Content Blurb | need backend | done
Widgets In Progress:
4 | [4.0] Featured Question (Category Specific) | html, css | done | Carl
7 | [7.0] Result List | html, css | done | Carl
10 | [10.0] Post a Question | html, css | done | Tim |  | 2012-07-23
12 | [12.0] Sub-Navigation | html, css and backend | in progress | Jason |  | 2012-07-24
Outstanding Widgets:
6 | [6.0] Content List |  |  | Jason | high | 2012-07-26
8 | [8.0] Manual List |  |  | Jason | high | 2012-07-27
11 | [11.0] Recent Activity | back end |  | Eddie | medium | 2012-07-26
| [11.0] Recent Activity | front end |  | Carl | medium
13 | [13.0] Promo | Hero/Media for Home Page |  |  | low
14 | [14.0] Ad | CQ5 |  |  | low
Complete Functionality:
0.5 | [0.5] Rate – Sebastian completed JavaScript that handles rating |  | done
0.7 | [0.7] Follow – Sebastian completed JavaScript that handles follow |  | done
Functionality in Progress:
0.2 | [0.2] Share – Harry is currently working on Add This integration |  | done
Outstanding Functionality:
0.2 | [0.2] Pagination | backend, (next previous html) |  | Eddie | high | 2012-07-27
0.3 | [0.3] Infinite Scroll | Can use pagination |  | ? | low
0.4 | [0.4] Flag | Custom tooltip with comment dropdown |  | Sebastian | high
0.6 | [0.6] Modal Window | Tim and Login |  | Tim | high | 2012-07-27
0.8 | [0.8] Tooltip | partial and java script |  | Sebastian | low
0.9 | [0.9] Click-down Content | profile and single pages. Shows expanded "read more" content |  | Tim | low
Other Outstanding Items
| Forms for login, register and sign up. |  | not started | Tim | high
| Code reviews for submitted widgets |  | not started | Brendan/Shafeeg
| Profile Pages |  | not started | Carl/Dan |  | 2012-07-27
| Single-post pages | Question, Article (Buying Guide, Blog) | not started | Sebastian | high | 2012-07-27
| QA Servers |  |  | Sebastian | high | 2012-07-26
| Open ID - Facebook | Facebook, Yahoo, Google, Twitter |  | Carl | medium | 2012-08-03