## Sheet1
Beta | 2012-08-22
Home Page
Basic Search
Login
Profile
Q&A
Moderation Tool
Blog/Buy Guide
Customer Service Page
Social Share
Experts & Badging
Comments
Iteration 1 | 2012-09-26
Migration
Following
Google Analytics
CSAT
Omniture Integration
Iteration 2 | 2012-10-17
Category Page Templates
Email Notifications (Responsys)
Badges
Profanity Filter
Iteration 3 | 2012-11-07
Ad Units
Polls
Iteration 4 | 2012-11-28
Smart Search
Add Manuals
Reviews and Ratings
Ability to Syndicate Q&A Widget to core sites