## Sheet1
| Completed Widgets: | Notes | Status | Assignee | Priority
1 | [1.0] Featured Blog Post |  | done
2 | [2.0] Featured Buying Guide |  | done
3 | [3.0] Featured Question (Landing Page) | need backend | done
5 | [5.0] Featured Team Members |  | done
9 | [9.0] Content Blurb | need backend | done
Widgets In Progress:
4 | [4.0] Featured Question (Category Specific) | Work by Carl Albrecht-Buehler started on 7/23 | not started
7 | [7.0] Result List | Work by Carl Albrecht-Buehler started on 7/19 | in progress
10 | [10.0] Post a Question | Work by Tim Steele started on 7/19 | done
12 | [12.0] Sub-Navigation | Work By Jason Corradino started on 7/23 | in progress
Outstanding Widgets:
6 | [6.0] Content List |  |  | Jason | high
8 | [8.0] Manual List |  |  | Jason | high
11 | [11.0] Recent Activity |  |  | Eddie
13 | [13.0] Promo | Hero/Media for Home Page
14 | [14.0] Ad | CQ5
Complete Functionality:
0.5 | [0.5] Rate – Sebastian completed JavaScript that handles rating |  | done
0.7 | [0.7] Follow – Sebastian completed JavaScript that handles follow |  | done
Functionality in Progress:
0.2 | [0.2] Share – Harry is currently working on Add This integration |  | done
Outstanding Functionality:
0.2 | [0.2] Pagination
0.3 | [0.3] Infinite Scroll
0.4 | [0.4] Flag | Custom tooltip with comment dropdown
0.6 | [0.6] Modal Window | Tim and Login
0.8 | [0.8] Tooltip |  |  | Sebastian | low
0.9 | [0.9] Click-down Content
Other Outstanding Items
| Forms for login, register and sign up. |  | not started | Tim
| Code reviews for submitted widgets |  | not started
| Profile Pages |  | not started | Carl/Dan
| Single-post pages |  | not started | Sebastian
Other Reasons for Concern
We are still having engineering discussions at the front end 10:15 stand-up that are lasting a half-hour to an hour and a half. There seems to still be confusion regarding what is necessary for the project.
The time required to develop on the front end is close to exceeding the time remaining before our 8/7 launch date.