## Sheet1
Completed Widgets:
1 | [1.0] Featured Blog Post
2 | [2.0] Featured Buying Guide
3 | [3.0] Featured Question (Landing Page)
5 | [5.0] Featured Team Members
9 | [9.0] Content Blurb
Widgets In Progress:
4 | [4.0] Featured Question (Category Specific) | Work by Carl Albrecht-Buehler started on 7/23
7 | [7.0] Result List | Work by Carl Albrecht-Buehler started on 7/19
10 | [10.0] Post a Question | Work by Tim Steele started on 7/19
12 | [12.0] Sub-Navigation | Work By Jason Corradino started on 7/23
Outstanding Widgets:
[6.0] Content List
[8.0] Manual List
[11.0] Recent Activity
[13.0] Promo
[14.0] Ad
Complete Functionality:
[0.5] Rate – Sebastian completed JavaScript that handles rating
[0.7] Follow – Sebastian completed JavaScript that handles follow
Functionality in Progress:
[0.2] Share – Harry is currently working on Add This integration
Outstanding Functionality:
[0.2] Pagination
[0.3] Infinite Scroll
[0.4] Flag
[0.6] Modal Window
[0.8] Tooltip
[0.9] Click-down Content
Other Outstanding Items
Forms for login, register and sign up.
Code reviews for submitted widgets
Profile Pages
Single-post pages
Other Reasons for Concern
We are still having engineering discussions at the front end 10:15 stand-up that are lasting a half-hour to an hour and a half. There seems to still be confusion regarding what is necessary for the project.
The time required to develop on the front end is close to exceeding the time remaining before our 8/7 launch date.